## Risk_Register
Risk ID | Risk Description | Probability (1-5) | Impact (1-5) | Risk Score | Mitigation Plan | Risk Owner | Status
R01 | API integration incompatibility during backend optimization | 3 | 5 | 15 | Run sandbox load and integration tests before merge | Tech Lead | Open
R02 | App Store / Play Store review exceeds expected timeline | 4 | 4 | 16 | Start store review process 10 days before go-live | Release Manager | Open
R03 | UI design approval delayed by business stakeholders | 2 | 3 | 6 | Hold weekly design sync meetings with Product Owner | Product Owner | Open
R04 | UAT feedback requires late-stage changes | 3 | 4 | 12 | Freeze change scope before UAT start | PMO Analyst | Open
R05 | OTP optimization introduces authentication regression | 2 | 5 | 10 | Run regression test pack before release | QA Lead | Open

## Stakeholder_Communication_Plan
Stakeholder | Role | Influence | Interest | Communication Type | Frequency | Owner
Digital Banking EVP | Sponsor | High | High | Steering Summary | Bi-weekly | PMO Analyst
Product Owner | Business Lead | High | High | Planning Meeting | Weekly | PMO Analyst
Backend Team | Delivery Team | High | Medium | Daily Standup | Daily | Scrum Master
Mobile Team | Delivery Team | High | Medium | Daily Standup | Daily | Scrum Master
QA Team | Quality Assurance | Medium | High | Test Status Review | Weekly | QA Lead
Sales & Support | Business Readiness | Medium | Medium | Release Readiness Brief | Before Go-Live | PMO Analyst