## MobileApp_WBS
WBS ID | Phase | Task Name | Owner | Start Date | End Date | Sprint
1 | Planning & Analysis | Requirement Review | Business Analyst | 2026-03-01 | 2026-03-03 | Sprint 1
1.1 | Planning & Analysis | UX Research & Feedback Review | Product Team | 2026-03-02 | 2026-03-05 | Sprint 1
1.2 | Planning & Analysis | Architecture Assessment | Tech Lead | 2026-03-04 | 2026-03-07 | Sprint 1
2 | Design | UI Prototype Design | UI/UX Designer | 2026-03-08 | 2026-03-12 | Sprint 2
2.1 | Design | Design Approval Cycle | Product Owner | 2026-03-10 | 2026-03-13 | Sprint 2
3 | Development | Backend API Optimization | Backend Team | 2026-03-14 | 2026-03-27 | Sprint 2-3
3.1 | Development | OTP Flow Improvement | Backend Team | 2026-03-14 | 2026-03-20 | Sprint 2
3.2 | Development | Homepage Refactoring | Mobile Team | 2026-03-21 | 2026-04-03 | Sprint 3-4
4 | Testing & QA | System Integration Testing | QA Team | 2026-04-04 | 2026-04-10 | Sprint 5
4.1 | Testing & QA | Security Testing | SecOps | 2026-04-07 | 2026-04-11 | Sprint 5
4.2 | Testing & QA | User Acceptance Testing | UAT Team | 2026-04-10 | 2026-04-14 | Sprint 5
5 | Deployment | Store Submission | Release Manager | 2026-04-15 | 2026-04-17 | Sprint 6
5.1 | Deployment | Go-Live Preparation | PMO Analyst | 2026-04-16 | 2026-04-18 | Sprint 6
5.2 | Deployment | Rollback Plan Validation | Release Manager | 2026-04-17 | 2026-04-19 | Sprint 6

## Sprint_Plan
Sprint | Sprint Goal | Start Date | End Date | Key Deliverables
Sprint 1 | Requirement validation and architectural review | 2026-03-01 | 2026-03-14 | Requirement list, architecture assessment
Sprint 2 | UI prototype and OTP optimization kickoff | 2026-03-15 | 2026-03-28 | Homepage mockups, OTP improvement tasks
Sprint 3 | Backend optimization and frontend refactoring | 2026-03-29 | 2026-04-11 | API improvements, dashboard components
Sprint 4 | Frontend completion and integration | 2026-04-12 | 2026-04-25 | Integrated mobile screens
Sprint 5 | QA, security checks, UAT | 2026-04-26 | 2026-05-09 | Test sign-off, UAT results
Sprint 6 | Store deployment and go-live readiness | 2026-05-10 | 2026-05-23 | Submission package, rollback checklist