## Risk_Register
Risk ID | Risk Category | Risk Description | Probability (1-5) | Impact (1-5) | Risk Score | Mitigation Plan | Risk Owner | Status
R-01 | Technical | System architecture incompatibility | 3 | 5 | 15 | Conduct architecture review before development | System Architect | Open
R-02 | Schedule | Development tasks take longer than planned | 4 | 4 | 16 | Add buffer time to development phase | Project Manager | Open
R-03 | Security | Unauthorized access to internal portal | 3 | 5 | 15 | Implement role-based access control (RBAC) | Security Engineer | Open
R-04 | Operational | File storage capacity exceeded | 2 | 4 | 8 | Implement storage monitoring and alerts | System Administrator | Open
R-05 | User Adoption | Employees do not actively use the portal | 3 | 3 | 9 | Provide training and onboarding sessions | Product Owner | Open
R-06 | Data Loss | System crash causing data loss | 2 | 5 | 10 | Enable automated daily database backups | DB Administrator | Open
R-07 | Integration | Email notification service failure | 3 | 3 | 9 | Implement retry logic and monitoring | Backend Developer | Open
R-08 | Compliance | Internal data handling policy violation | 2 | 4 | 8 | Implement audit logs and compliance review | Compliance Officer | Open

## Risk_Matrix
Impact ↓ / Probability → | 1 | 2 | 3 | 4 | 5
5 | Low | Medium | High | High | Critical
4 | Low | Medium | High | High | Critical
3 | Low | Medium | Medium | High | High
2 | Low | Low | Medium | Medium | High
1 | Low | Low | Low | Medium | Medium