## Sprint_Plan
Sprint | Sprint Goal | Start Date | End Date | Story IDs
Sprint 1 | User authentication and user management setup | 2026-03-01 | 2026-03-14 | US-01, US-02, US-12, US-13
Sprint 2 | Announcement module and notification infrastructure | 2026-03-15 | 2026-03-28 | US-03, US-04, US-14
Sprint 3 | Document management and file versioning system | 2026-03-29 | 2026-04-11 | US-05, US-06, US-07, US-08
Sprint 4 | Appointment scheduling and approval workflow | 2026-04-12 | 2026-04-25 | US-09, US-10, US-11

## Product_Backlog
Story ID | Epic | User Role | User Story | Acceptance Criteria | Priority | Story Points | Sprint
US-01 | Authentication | Employee | As an employee I want to securely log in to the portal so that I can access internal resources | Valid username/password required; Session created; Incorrect credentials show error | High | 5 | Sprint 1
US-02 | Authentication | Employee | As a user I want to reset my password so that I can regain access if I forget it | Reset link sent via email; Password must meet security policy | Medium | 3 | Sprint 1
US-03 | Announcement Module | Admin | As an admin I want to create announcements so that employees can see important updates | Title required; Content field required; Publish button visible | High | 5 | Sprint 2
US-04 | Announcement Module | Employee | As an employee I want to view announcements so that I stay informed about company news | Announcements listed by date; Click opens detail page | High | 3 | Sprint 2
US-05 | Document Management | Employee | As an employee I want to upload documents so that I can share files with my department | File size validation; Upload success notification | High | 8 | Sprint 3
US-06 | Document Management | System | As a system I want to assign version numbers to uploaded files so that document history is preserved | Version number incremented automatically | Medium | 5 | Sprint 3
US-07 | Document Management | Department Manager | As a manager I want to approve uploaded files so that only valid documents are published | Approve/Reject buttons available; Notification sent to uploader | Medium | 5 | Sprint 3
US-08 | Document Management | Employee | As a user I want to view document version history so that I can track file updates | Version list available; Previous versions downloadable | Low | 3 | Sprint 3
US-09 | Appointment Module | Employee | As an employee I want to request a meeting with a department manager so that I can schedule discussions | Date selection required; Description field required | High | 5 | Sprint 4
US-10 | Appointment Module | System | As a system I want to check calendar availability so that double booking is prevented | Calendar availability checked before request submission | High | 3 | Sprint 4
US-11 | Appointment Module | Department Manager | As a manager I want to approve or reject appointment requests so that I control my schedule | Approve/Reject actions available; Notification sent | High | 5 | Sprint 4
US-12 | User Management | Admin | As an admin I want to create new user accounts so that employees can access the portal | User form required fields; Role assignment mandatory | High | 5 | Sprint 1
US-13 | User Management | Admin | As an admin I want to assign roles to users so that permissions are controlled | RBAC applied; Role stored in database | High | 3 | Sprint 1
US-14 | Notification | System | As a system I want to send notifications when actions occur so that users stay informed | Email or in-app notification triggered | Medium | 3 | Sprint 2