## WBS_Task_List
WBS ID | Phase | Task Name | Owner | Start Date | End Date | Duration (Days)
1 | Project Initiation | Project Kickoff Meeting | Project Manager | 2026-02-01 | 2026-02-02 | 2
1.1 | Project Initiation | Stakeholder Identification | Business Analyst | 2026-02-02 | 2026-02-03 | 2
1.2 | Project Initiation | Initial Requirement Gathering | Business Analyst | 2026-02-03 | 2026-02-05 | 3
2 | Analysis | Process Analysis (AS-IS) | Business Analyst | 2026-02-06 | 2026-02-08 | 3
2.1 | Analysis | Requirement Documentation (BRD) | Business Analyst | 2026-02-08 | 2026-02-12 | 5
2.2 | Analysis | User Story Creation | Business Analyst | 2026-02-12 | 2026-02-14 | 3
3 | Design | System Architecture Design | System Architect | 2026-02-15 | 2026-02-18 | 4
3.1 | Design | UI/UX Mockup Creation | UI Designer | 2026-02-18 | 2026-02-20 | 3
3.2 | Design | Database Schema Design | Backend Developer | 2026-02-20 | 2026-02-22 | 3
4 | Development | Backend API Development | Backend Developer | 2026-02-23 | 2026-03-05 | 11
4.1 | Development | Frontend Portal Development | Frontend Developer | 2026-02-23 | 2026-03-07 | 13
4.2 | Development | Document Management Module | Backend Developer | 2026-03-01 | 2026-03-08 | 8
4.3 | Development | Appointment Scheduling Module | Backend Developer | 2026-03-03 | 2026-03-10 | 8
5 | Testing | System Integration Testing | QA Engineer | 2026-03-11 | 2026-03-15 | 5
5.1 | Testing | User Acceptance Testing (UAT) | QA Engineer | 2026-03-15 | 2026-03-18 | 4
6 | Deployment | System Deployment | System Administrator | 2026-03-19 | 2026-03-20 | 2
6.1 | Deployment | User Training | Session Trainer | 2026-03-21 | 2026-03-22 | 2

## Timeline_Gantt
Task Name | Start Date | End Date | Duration
Project Kickoff Meeting | 2026-02-01 | 2026-02-02 | 1
Stakeholder Identification | 2026-02-02 | 2026-02-03 | 1
Requirement Gathering | 2026-02-03 | 2026-02-05 | 2
Process Analysis | 2026-02-06 | 2026-02-08 | 2
BRD Documentation | 2026-02-08 | 2026-02-12 | 4
User Story Creation | 2026-02-12 | 2026-02-14 | 2
System Architecture Design | 2026-02-15 | 2026-02-18 | 3
UI Mockup Design | 2026-02-18 | 2026-02-20 | 2
Database Design | 2026-02-20 | 2026-02-22 | 2
Backend Development | 2026-02-23 | 2026-03-05 | 10
Frontend Development | 2026-02-23 | 2026-03-07 | 12
Module Integration | 2026-03-01 | 2026-03-10 | 9
System Testing | 2026-03-11 | 2026-03-15 | 4
User Acceptance Testing | 2026-03-15 | 2026-03-18 | 3
Deployment | 2026-03-19 | 2026-03-20 | 1
User Training | 2026-03-21 | 2026-03-22 | 1